## Assignment 1
Iteration 1, 4 wks | Iteration 2, 4 wks | Iteration 3, 4 wks
UC01, UC02, UC04 | UC03, UC05, UC06 | UC07, UC08, UC09
3pt, 5pt, 4 pt | 3pt, 3pt, 6pt | 4pt, 4pt, 4pt
P3, P2, P3 | P1, P3, P1 | P4, P2, P1
dep: NA | dep: UC01, UC02 | dep: UC04, UC03, UC06,

## Lab 1
UC01 | Search for Programs | 2 | Reuse of prewritten algorithms
UC02 | Display Program Detail | 4 | Uses data from UC01, but detailed programs require technical expertise
UC03 | Submit Online Application | 3 | Form built using template
UC04 | Login | 2 | Requires access and verification
UC05 | Logout | 2 | Verifies activities, ensures user has ended tasks
UC06 | Edit Online Application | 2 | Based on user function, template perfomrance
UC07 | Check Application Status | 2 | User able to verify status, system updates status based on input
UC08 | Submit Reccomendation | 3 | User input reflects time consumption
UC09 | Approve Course Equivalency Form | 3 | Numerous forms require separate approvals

## Risks
Risk 1 | User Account Access | Ensure user's account is active, operable; verify database information
Risk 2 | Program Selection | Ensure the correct program is used and used correctly
Risk 3 | Application Errors | Ensure that applications are filled correctly, verify; ensure data is stored properly in correct locations
Risk 4 | Course Errors | Ensure courses are applicable, available; verify course database is functioning
Risk 5 | Form Submission | Ensure forms are filled out, submitted correctly; verify forms are sent to proper channels once submitted